WorkflowMAX  Pimple Model: MVP Outbound Campaign

SOP for CRO Review  |  June 2026  |  Prepared by Sina Zarei

What This Is

A 4-week experiment running 6 email/SMS touchpoints over 18 days per contact. Each touchpoint delivers a piece of interactive content designed to make prospects self-assess their operational gaps before an AE reaches out. Engagement signals feed a lead score that determines when and how the AE engages.

Campaign Parameters

| Region | Australia (prototype before UK/US) |
| --- | --- |
| Personas | CEO, MD, CFO, COO at firms with 20-200 staff |
| Volume | 150 companies / ~250 contacts total (~125 per AE) |
| Stagger | 50 contacts/day across Mon-Fri of week 1 |
| Total cost | $213-326 USD (HeyGen $138 + Clay $75-188) |
| Launch | June 8, 2026 |
| Duration | 4 weeks (June 8 - July 4) |

Vertical Split

| AE | Verticals |
| --- | --- |
| Sina | Management & Business Consulting, Creative & Marketing, Civil & Infrastructure |
| Denzel | Architecture & Design, Engineering Consultancy, Construction & Trades |

6-Touchpoint Sequence (18 days per contact)

| TP | Day | Channel | Content | Subject Line |
| --- | --- | --- | --- | --- |
| 1 | 1 (Tue) | Email | AI video + Workflow Health Check | Quick question about how [Company] tracks job profitability |
| 2 | 5 (Fri) | Email | Profit Leak Calculator | The 5 places [industry] firms lose money without realising |
| 3 | 9 (Tue) | SMS* | Firm Benchmark tool | SMS: 2026 benchmarks for [industry] firms your size |
| 4 | 12 (Fri) | Email | 12-min demo video landing page | 12 minutes. Quote to invoice in one platform. |
| 5 | 15 (Tue) | Email | Firms Like Yours (case studies) | How [similar firm type] firms are running jobs differently |
| 6 | 18 (Fri) | Email | Breakup recap with all links | Last one from me, [First Name] |

*SMS on TP3 is conditional on prior engagement (opened/clicked TP1 or TP2). Non-engagers receive email instead.

Lead Scoring (Pimple Model)

| Action | Points | Notes |
| --- | --- | --- |
| Email open | +5 | Low intent signal |
| Link click (email or SMS) | +15 | Moved to landing page |
| Content interaction (complete health check, use calculator, etc.) | +25 | Deep engagement |
| Booking link clicked | +50 | Self-serve intent |

| Tier | Score | Action |
| --- | --- | --- |
| Cold | 0-24 | Sequence continues. No AE action. |
| Warm | 25-64 | AE notified via HubSpot. Sequence continues. |
| Hot | 65-99 | Sequence pauses. AE task created. Outreach within 24hrs. |
| Eruption | 100+ | Sequence stops. AE calls within the hour. |
| Dead | <25 post-TP6 | 90-day nurture hold. Re-enter in wave 2. |

Success Criteria (from 250 contacts, $20K avg ACV)

| Metric | Realistic | Good | Exceptional |
| --- | --- | --- | --- |
| TP1 email open rate | 25-30% | 35% | 45%+ |
| TP1 click-through (of openers) | 8-10% | 15% | 20%+ |
| Health check completion (of clickers) | 30-35% | 40% | 50%+ |
| Hot leads (65+ score) | 4-6 | 8-10 | 12+ |
| Meetings booked | 2-3 | 4-6 | 8+ |
| Pipeline generated | $40-60K | $80-120K | $160K+ |
| Cost per meeting | <$120 | <$60 | <$40 |

Timeline

| Week | Activity |
| --- | --- |
| Jun 2-6 | Finalise content, Leo builds HubSpot workflows/properties, video script template |
| Jun 8-13 | Campaign live. 50 contacts/day. Monitor deliverability and open rates. |
| Jun 16-20 | First hot leads surface. AE outreach begins on triggered leads. |
| Jun 23-27 | Bulk of journeys complete. Final hot leads. Breakup emails land. |
| Jun 30-Jul 4 | Buffer week. AE follow-up. Full data review. Wave 2 iteration decisions. |

Interactive Content Pieces (all built, mobile-first, WFM branded)

| TP | Piece | What It Does |
| --- | --- | --- |
| 1 | Workflow Health Check | 8 scenario-based questions. Scores maturity (Reactive/Structured/Optimised). Returns vertical-specific recommendations. Firm size comparison. |
| 2 | Profit Leak Calculator | Step-by-step flow modelling 5 compounding leaks. Shows individual + total dollar impact. 'You don't need to fix everything' insight. Two models: services + project. |
| 3 | Firm Benchmark | 4 key metrics with avg vs top performer. Self-placement selector updates gap cost in real time. 'Closing half the gap' synthesis. Share button. |
| 4 | Demo Landing Page | YouTube embed (12-min walkthrough) with chapter markers. Thumbnail-first with play button. Booking CTA. |
| 5 | Firms Like Yours | Vertical-filterable case studies with YouTube testimonial embeds, outcome badges, pull quotes. Needs real customer data. |

Decision Criteria

Scale to wave 2 (500+ contacts): If we generate 4+ hot leads and book 2+ meetings from 250 contacts.

Iterate: If open rates below 25% (revisit subject lines), click-through below 6% (revisit copy), or completion below 25% (revisit UX). Review weekly with Leo.

Stop: If fewer than 3 total content interactions across all 250 contacts by end of week 2. Pause and diagnose before burning more contacts.

Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| CRO | Ryan |  |  |
| AE | Sina Zarei |  |  |
| AE | Denzel |  |  |
| GTM Engineer | Leo |  |  |